## TestCases
Test Suite/ Scenario | TestCaseID - Name | Priority | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail/Blocked | BUG number
Interfata de LOGIN | Test 1 - User name si parola corecta + buton login | p1 | deschide browserul go to login page introdu username valid introdu parola valida click on login | username:performance_glitch_user password:secret_sauce | Browserul te duce pe Main Page | Browserul te duce la main page | Pass
| Test 2 - User name corect si parola incorecta + buton login | p1 | deschide browserul go to login page introdu username valid introdu parola incorecta click on login | username:performance_glitch_user password:secret_sauce1 | Error message: Epic sadface: Username and password do not match any user in this service | Error message: Epic sadface: Username and password do not match any user in this service | Pass
| Test 3 - User name camp gol si parola corecta +buton login | p1 | deschide browserul go to login page username camp gol introdu parola corecta click on login | username:camp gol password:secret_sauce | Error message: Epic sadface: Username is required | Error message: Epic sadface: Username is required | Pass
| Test 4 - User name corect si parola camp gol + buton login | p1 | deschide browserul go to login page username corect parola camp gol click on login | username:performance_glitch_user password: camp gol | Error message: Epic sadface: password is required | Error message: Epic sadface: password is required | Pass
Pagina de produs | Test 5 - Verificarea lista produse | p2 | deschide browserul login with valid credentials go to main page click on products | username:performance_glitch_user password:secret_sauce | the page should show a list with all 6 products | the page show a list with all 6 products | Pass
| Test 6 - Testare detalii in produs individual | p2 | deschide browserul login with valid credentials go to main page click on products click on details | username:performance_glitch_user password:secret_sauce | it should show a new "form"with details about the product | it should a new "form"with details about the product | Pass
| Test 7 - Testare buton 'back to all products' | p2 | deschide browserul login with valid credentials go to main page click on products click on one product click on "back to all products" | username:performance_glitch_user password:secret_sauce | the page should redirect to back to all products | the page redirect back to all products | Pass
| Test 8 - Testare buton de sortare de la A la Z | p2 | deschide browserul login with valid credentials go to main page click on products click on "sort" select "from A to Z" | username:performance_glitch_user password:secret_sauce | the products should be sorted by alphabetical order from A to Z | the products is sorted by alphabetical order from A to Z | Pass
| Test 9 - Testare buton de sortare de la Z la A | p2 | deschide browserul login with valid credentials go to main page click on products click on "sort" select "from Z to A" | username:performance_glitch_user password:secret_sauce | the products should be sorted by alphabetical order from Z to A | the products is sorted by alphabetical order from Z to A | Pass
| Test 10 - Testare buton de sortare dupa pret crescator | p2 | deschide browserul login with valid credentials go to main page click on products click on "sort" select "ascending " | username:performance_glitch_user password:secret_sauce | the products should be sorted by ascending price | the products is sorted by ascending price | Pass
| Test 11 - Testare buton de sortare dupa pret descrescator |  | deschide browserul login with valid credentials go to main page click on products click on "sort" select "descending" | username:performance_glitch_user password:secret_sauce | the product should be sorted by descending price | the product is sorted by descending price | Pass
| Test 12 - Testare buton "add to cart" cu un singur produs |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" | username:performance_glitch_user password:secret_sauce | one product should be added to cart | one product is added to cart | Pass
| Test 13 - Testare buton "add to cart" cu 6 produse (toate) |  | deschide browserul login with valid credentials go to main page click on products select 6 products click "add to cart" | username:performance_glitch_user password:secret_sauce | 6 products should be added to cart | 6 products are added to cart | Pass
| Test 14 - Testare buton "remove from cart" din main list |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go back to main page click on "remove from cart" | username:performance_glitch_user password:secret_sauce | the product should be deleted from cart | the product is deleted from cart | Pass
Interfata checkout | Test 15 - Testare "Checkout" cu date corecte client |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "checkout" enter valid credential | username:performance_glitch_user password:secret_sauce | the page should redirect to the form "checkout" | the page redirect to the form "checkout" | Pass
| Test 16 - Testare "Checkout " cu date incomplete client |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "checkout" enter incomplete credential | username:performance_glitch_user password:secret_sauce | the page should show an error "Error: First Name is required" | the page show an error "Error: First Name is required" | Pass
| Test 17 - Testare buton "Continue" din pagina de checkout |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "checkout" enter complete and valid credential click on "continue" | username:performance_glitch_user password:secret_sauce | the page should be redirect to "checkout overview" | the page is redirected to "checkout overview" | Pass
| Test 18 - Testare buton "Cancel" din pagina de checkout |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "checkout" enter complete and valid credential click on "cancel" | username:performance_glitch_user password:secret_sauce | the page should redirect to "list of products" | the page redirect to"cart" | Fail | BUG9
| Test 19 - Testare buton "Finish" din pagina de checkout |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "checkout" enter complete and valid credential click on "finish" | username:performance_glitch_user password:secret_sauce | the page should comfirm the order is been placed | the page comfirm the order has been placed | Pass
Cosul de cumparaturi | Test 20 - Testare buton "remove" from cart |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "remove" | username:performance_glitch_user password:secret_sauce | the product should be removed from cart | the product is removed from cart | Pass
| Test 21 - Testare buton "continue shopping" |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "continue shopping" | username:performance_glitch_user password:secret_sauce | the page should redirect to back to all products | the page is redirected back to all products | Pass
| Test 22 - Testare buton "checkout" |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "checkout" | username:performance_glitch_user password:secret_sauce | the page should redirect to checkout page | the page is redirected to "checkout" page | Pass
| Test 23 - Testare detalii produse din cosul de cumparaturi |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on details on a product | username:performance_glitch_user password:secret_sauce | the page should show the details of that product | the page show the details of that product | Pass
Finalizare comanda | Test 24 - Testare buton "back to home" |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "checkout" enter complete and valid credential click on "finish" click on "back to home" | username:performance_glitch_user password:secret_sauce | the page should redirect to back to all products | the page is redirected back to all products | Pass
LOGOUT | Test 25 - Testare buton "logout" din main page |  | deschide browserul login with valid credentials go to main page click on "meniu" click on "logout" | username:performance_glitch_user password:secret_sauce | the page should redirect to login page | the page is redirected to login page | Pass
| Test 26 - check if the products added to cart are saved if you logout and login again |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" click "back main page" click on "meniu" click "logout" login with valid credentials go to maijn page click on "cart" | username:performance_glitch_user password:secret_sauce | the products should still be in the cart | the products are still in the cart | Pass
Time performance | Test 27 - Login time performance |  | deschide browserul go to login page introdu username valid introdu parola valida click on login | username:performance_glitch_user password:secret_sauce | the login time should be 1 second | the login time has a delay of 7 seconds | Fail | BUG10
| Test 28 - Testare buton 'back to all products' - time performance |  | deschide browserul login with valid credentials go to main page click on products click on one product click on "back to all products" | username:performance_glitch_user password:secret_sauce | time performance should take less the 1 second | the time performance has a delay of 7 seconds | Fail | BUG11
| Test 29 - Testare buton de sortare de la A la Z - time performance |  | deschide browserul login with valid credentials go to main page click on products click on "sort" select "from A to Z" | username:performance_glitch_user password:secret_sauce | time performance should take less the 1 second | the time performance has a delay of 7 seconds | Fail | BUG12
| Test 30 - Testare buton de sortare de la Z la A - time performance |  | deschide browserul login with valid credentials go to main page click on products click on "sort" select "from Z to A" | username:performance_glitch_user password:secret_sauce | time performance should take less the 1 second | the time performance has a delay of 7 seconds | Fail | BUG13
| Test 31 - Testare buton de sortare dupa pret crescator - time performance |  | deschide browserul login with valid credentials go to main page click on products click on "sort" select "ascending " | username:performance_glitch_user password:secret_sauce | time performance should take less the 1 second | the time performance has a delay of 7 seconds | Fail | BUG14
| Test 32 - Testare buton de sortare dupa pret descrescator - time performance |  | deschide browserul login with valid credentials go to main page click on products click on "sort" select "ascending " | username:performance_glitch_user password:secret_sauce | time performance should take less the 1 second | the time performance has a delay of 7 seconds | Fail | BUG15
| Test 33 - Testare buton "continue shopping" din cosul de cumparaturi - time performance |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "continue shopping" | username:performance_glitch_user password:secret_sauce | time performance should take less the 1 second | the time performance has a delay of 7 seconds | Fail | BUG16
| Test 34 - Testare buton "back to home" from Checkout:Complete!" - time performance |  | deschide browserul login with valid credentials go to main page click on products click "add to cart" go to cart click on "checkout" enter complete and valid credential click on "finish" click on "back to home" | username:performance_glitch_user password:secret_sauce | time performance should take less the 1 second | the time performance has a delay of 7 seconds | Fail | BUG17

## Results
Total tests | Nb of Pass test | Nb of Failed test | Nb. Of Blocked tests | Total test covered | Blocked Tests% | Failed test% | Pass test % | Total test covered
3 | 3 | 0 | 0 | 3 | 0 | 0 | 100 | 100